## Sheet1
PLATEAU STATE INFRASTRUCTURE PROMOTION AND REGULATORY AGENCY
PUBLIC PRIVATE PARTNERSHIP
STATE PROJECT STATUS REPORT AS @ JULY 2023
Solicited Projects
Unsolicited Projects
S/N | PROJECT NAME | PROJECT DESCRIPTION | RELEVANT MDA(S) | AGENCY'S ROLE/INPUT | CURRENT STATUS/RECOMMENDATION
1 | Plateau State Geographic Information System Upgrade | The PLAGIS Project was occasioned by the needs of the people and government of Plateau State to better manage and administer land and land-related resources of the state.PLAGIS is a sysytem that computes all information on all Plateau State Land in a functional digital format. | Ministry of Lands and Survey | 1. Agency reviewed for inception report! Draft concept note and feasibilty study to be carried out 2. Received the Next Phase draft on PLAGIS from Director of Lands. Need to assess investment injection requirements for private sector participant in line with PPP | Received the Project Inception report and technical & Labour project costing requiring estimated N300mill to complete project for yr 1 setup operations Only. Project Concept note in line with current needs to be developed with proper feasibilty assessment if PPP can be utilised to achieve this.
2 | Plateau State Potato Value Chain | The Potato Value Chain Support Project involves construction and rehabilitation of critical infrastructure (access roads, culverts, small earth dams, diffused storage stores, community markets, processing units among others) to reduce agricultural production costs and enhance market access | Federal Ministry of Agriculture, Plateau State Ministry of Agriculture, Africa Development Bank (Financier) | 1. The Agency reviewed some documents of this project which include Appraisal Report, Loan Agreement, Report of AfDB Supervision. Upon review, the Agency requested for the current status of the project from the Project Coordinator since the Africa Development Bank extended their agreement on this project & got updated report on the AfDB website. | About 85% of the infrastructure has been developed. The Agency is yet to get a detailed report on the current status of the project to be able to adequately prepare project for PPP as required by AfDB. Next steps: Agency needs to conduct proper due diligence on the project current status, progress and private partner incentives.
3 | Constitution of Technical Committee on Government Organised Private Sector Initiatives in Plateau State | This committe is aimed at promoting and encouraging collective vision for the creation of an enabling business environment and robust economy, driven by the organized private sector to achieve sustainable development | Office of the SGS, Min. Transport, Min Environment, Min Commerce, Min. Environment, Min. Water Resources, Min. Finance, Min. Works, Min Education (Higher & Secondary), Min Tourism, Organized Private Sector operating in Plateau State | Several meetings were held at the SGS Office Old Government house with the Organized Private Sector. Each private participant did a presentation on their expectation from the government and also the achievements they have made in the State so far. DG PPP was appointed secretary of this committee and one of his roles include consolidaiton of the report for the entire group based on the defined Terms of Reference (ToR). | Agency is compiling submissions made by Organized Private Sector on the Plateau. It is strongly recommended that new administration continue this initiative as these are primary the current investors in the State. The SGS was the Chairman of this Technical Committee made up of both Public (Key Econoomic Commissioners/MDAs) and Private parties. The Agency DG is the Secretary of the committtee.
4 | Redevelopment and Enhancement of the Jos Main Market, Terminus, | Reconstruction of a modern, multi-level market structure replete with shops, open and lock-up stalls, cinema and lounge and other ancillary facilities. | Ministry of Commerce & Industry, Jos Main Market Authority, PMRDO | 1. The Agency received and reviewed documents developed by the relevant MDAs on this project with an estimated project value of about N10 Billion. 2. Agency was instrumental in advising on the stakeholders's engagement which displayed public concern for the project both at the end of the administrations tenure as well as the religious connotations as intepreted by the public hence a litigation court case was filed. | 1. Pending Court Injuction 2. Agency to reassess project detailed Future concept, feasibility study, project viability & valuation plus EIA review as well as investor assess appetite in current economic climate.
5 | Deployment of Solar Power Solutions | Providing access to solar power solutions through the sale of Solar Home Systems. | Ministry of Water Resources and Energy, Wavelength Integrated Power Services Limited | 1. The Agency received and reviewed proposal documents submitted by the private partner. 2. The signed agreement of this project is under the Agency's custody. 3 .Agency has written the Ministry of Water Resources and Energy to set up project committee, make the agency a member and have also requested for the status of the project since the committee was not constituted. The MDA have failed to provide agency with intended communities selected to benefit from this intervention and the clear repayment model as it might impact the communities impacted etc. The project value is around N1.5Billion. | 1. Memorandum of Understanding between Wavelength Integrated Power Services Limited and Plateau State Government was signed on the 25th August 2022 based on REA initiative 2. The private partner (Wavelength Integrated Power Service Ltd ) is yet to secure funding to implement this project and Agency needs to reassess current project viability, community impact etc with Ministry of Water Resources & Energy.
6 | Plateau State Liaison Office In Lagos | Development of facilities under Plateau State Liaison Office in Lagos | Secretary to Government of State | 1. The Agency is to get the current title documents of this property from the State Government 2. Assess best use of facility for development facing Eko Atlantic and other requirements - Get current valuation of the Asset also | 1. Full settlement & Payment of statutory levies to Lagos State Government. & any Outstanding balance with Benue State Government. 2. Reassess possible best use for asset to Develop concept note and feasibilty study where necessary. This is a prime location that can yield much economic value to the State.
7 | Medium Density Housing Estate Property, Bukuru | Renovation of existing Properties (2 Bungalows and 1 Boy’s Quarters) and construction of 12 Properties bedroom Flats on the existing land of 1.8 hectares | Jos Water Service Corporation, Zazzaga NIG.Ltd (Proposed private partner) | 1. Private partner submitted project proposal and it was reviewed by the Agency 2. Received valuation report and title documents of this property from the MDA 3. The Agency also provided a template of concept note development to the MDA 3. Requested for the status update on this project from the MDA. | The Agency is yet to receive the current status of this project from Jos Water Corporation Services. Agency learnt that the project development is on-going however the Agency had not approved the go ahead with the MDAs. An agreement was also signed but no copy was made available to the Ministry of Juctice or Agency. The is need to stop this development and revisit the agreement entered into by the MDA without final authorisation for a partnership.
8 | Plateau State University Teaching Hospital - Proposed Legacy Project upgrade | Financing and Development of a 200bed capacity, teaching hospital in Shendam LGA to serve as an academic medical centre and secondary healthcare facility to various areas of Plateau State and the wider Middle Belt of Nigeria. | Ministry of Health | 1. The Agency attended several meetings on the development of this project by CPL, Abuja on the Shendam Legacy project. 2. Draft Concept Note was developed by the Agency with the Ministry. The feasibility assessment was to be carried out by the Private Party! | This project was stopped as it was considered selected infrastructure was not adequately designed to accomodate a Teaching Hospital and a lot of restructuring will be required. It was not also clear on the financial modelling and implications on the State.
9 | Construction of Administration Block | Construction of a new administration block at the Plateau State College of Nursing & Midwifery Vom | Plateau State College of Nursing & Midwifery Vom | 1. Agency received a document from the Plateau State College of Nursing & Midwifery Vom that had a list of proposed infrastructure projects and advised that the MDA should pick one that is priority 2. Agency provided a project concept note template for the MDA to develop further and a clear indication of priority sections of the required private sector interventions that can be attractive and repaid back from MDA operations. | The MDA is currently working on the project concept note and yet to submit scope of project plus cost implications to the Agency. Project to be further developed by MDA.
10 | Development of Indoor Theatre | Completion and renovation of the existing Indoor Theatre | Ministry of Tourism, Hospitality & Culture | The Agency reviewed the asset and the Title for this asset could not be located in Ministry of Lands etc The Agency is currently assisting the MDA to on Concept note development for this project. Agency requested from the Lands to locate the title documents or advise on how to proceed to get valiud titles documents for the asset. | Draft concept note. Agency to carry out detailed valuation of asset, concept and feasibilty/Viability study to ascettrain best use of asset for PPP or Privatisation etc.
11 | Heipang Inland Depot | Completion of the existing ICD infrastructure, access roads and restricted entrances and exits, cargo handling equipment , vehicles, plants and machinery | Ministry of Commerce & Industry/PIPC | The Agency was engaged to monitor the trasfer process of acquiring the asset from the private partner on behalf the State which was purchased for N2.2Billion. Ownership of the ICD asset within PLSG is not too clear. | A proper assessment needs to be done in line with EPZ and Agro industrial zone & Cargo Airport to get the best value for this asset going forward. A Proper Concept note and feasibility study also needs to be carried out for best use of asset.
12 | Grain Storage Project | Establishment of grain storage facilities to handle a variety of agricultural commodities, including whole grains such as corn, soybeans, wheat, barley, rice, | Ministry of Agriculture | This iniative was copied from other similar projects in neighbouring states. There are several moribound assets in the Ministry of Agriculture that have been identified can be used for such purposes in line with Food Security Challenges etc. Agency is assisting in the development of concept note for this project. | Draft concept note. Agency to carry out the feasibilty study and ascertain best use of the moribund storehouses for this project and map out locations with the MDA across 17 LGAs.
13 | Plateau State Strategic Minerals Project | Establishment of a mineral resource processing centre in the State | Plateau State Mineral Development Company | Agency proposed project for value addition in the Mining Value Chain and has drafted a project concept note for this purpose. Yet to be discussed with relevant MDAs | Draft concept note. Agency to carry out needs assessment and feasibility study.
14 | Jos Tourist City | Redevelopment of Jos Wildlife Park, Mado Tourist Village and Solomon Lar Park to Jos Tourist City | Plateau State Tourism Corporation | Agency initiated project with initial discuss with MDA and guidance on need for development of project concept note, assets valuations, title document validation based on current status as well as feasibility studies and project preparation documentation. | Agency awaiting response from Plateau State Tourism Corporation concerning information requested to develop this project further.
15 | Proposed Blocks of 322 lock-up shops/10 Warehouse at Abattoir market, Jos South LGA. | Construction and fencing of 322 lock-up shops/ 10 warehouses at Abattoir market, Jos South LGA | Ministry of Agriculture, Ministry of Lands & Survey, Unsolicited proposal by Russso Minerals Limited | 1. Agency received and reviewed project proposal from Russo Minerals 2. Wrote to the ministry of Agriculture to provide current valuation and title documents for the Abattoir Property. 3. Wrote to the private partner concerning the missing title documents for this property. | 1. The title documents for this property are yet to be found. 2. If missing titles can not be located, we advocate a new site plan and registration of the property be carried out, valuation etc to enable private partner engagement
16 | Development of the Abattoir | Development of the existing abattoir & livestock value chain | Ministry of Agriculture, Unsolicited Project by West South Atlantic Company PTY LTD (Based in South Africa) | 1. The Agency received a letter of interest from West South Atlantic Company (based in South Africa) on livestock value chain development in the State 2. Requested for development of project Concept Note from Ministry of Agriculture and also title documents of the Abattoir | 1. The title documents for this property are yet to be found. 2. If missing title can not be located, we advocate a new site plan and registration of the property be carried out to enable private partner engagement
17 | Green Growth : Forest Reserves | This project involves tree nursery setup in all local government areas where the reserves are located also restoration of depleted forest reserves | Ministry of Environment, Unsolited Project by Green Sahara | 1. The Agency provided guideline for PPP Project Proposal to the Private Partner. 2. The private partner submitted documents on this project which the Agency reviewed and also requested for a feasibility from the private partner 3. The Agency is to identify specific quick wins and locations that will be used as a pilot project for this intervention and green agenda | Determinining Project Scope as well as Pilot schemes is essential for preliminary assessments & feasibility study of this project Private Partner.
18 | Restructuring, Rehabilitation, Redevelopment and Operation of Panyam Fish Farm | Rehabilitation of 39 existing fish ponds, upgrading existing structures and equipment which include administration block, hatchery, feed mills, store house, staff quarters etc | Ministry of Agriculture, Ministry of Justice, Unsolicited Project by Amborg Investment Ltd | 1. From the preliminary review of documents submitted by the private partner (Amborg Investment Limited), the agency noticed that the Private Partner has not displayed Technical and Financial capacity to carry out this project. 2. The agency also discovered that the following documents are not provided (i) Pre-feasibility/study analysis (ii) Detailed Concept Note clearly defining the scope of the project (iii) Copies of all current legal titles covering Panyam Fish Farm (land titles, valuation reports & available equipment) (iv) Infromation/ Report on the status of the suit between Solbec Ltd & PLS, this information is to be provided by the Ministry of Agriculture. | 1. The Agency is yet to receive requested documents information from the Ministry of Agriculture 2. The pending suit case needs to be resolved and project properly reassesed for private partner participation including cfinalising on draft concept note, conducting a proper asset valuation, feability and best case scenario assessment for use of Asset going forward.
19 | Deployment of Plateau Health Information Management System Enterprise | Deployment of Plateau Health Information Management System Enterprise | Ministry of Health, Unsolicited project by Oracode Limited | 1. Agency requested for a full project documentation, project status and signed MOU from the Ministry of Health since the project was initiated without communication to the Agency 2. Copy of the MOU is in the Agency's custody | 1. Agency reviewed only a photocopy of the signed MOU from Ministry of Health 2. Yet to receive report on current status of the project and full project documentation from the Ministry of Health.
20 | Deployment of Information Management System Portal | Deployment of a consolidated Information Management System Portal for the purpose of registration of business premises, renewal of business and issuance and renewal of licences and central control of business premises | Ministry of Commerce, Unsolicited project by Oracode Limited | 1. Agency requested for a full project documentation, project status and signed MOU from the Ministry of Commerce & Industry since the project was initiated without communication to the Agency 2. Copy of the MOU is in the Agency's custody | 1. Agency yet to reviewed a report on current status of the project and full project documentation from the Ministry of Commerce & Industry.
21 | Deployment of One Education Project | (DEPLOYMENT OF ONE EDUCATION PROJECT)For the Deployment of a consolidated State Education Management Information System (SEMIS) for the Purpose of Super Managing School (Basic and Secondary)Admnistration and Education Service Delivery System within Plateau State | Ministry of Education (Basic, Secondary), Aspire Univas Intersystems International | 1. MOU of this project is in Agency's custody 2. Agency requested for the current status of the Project from the Ministry of Education (Basic, Secondary) | MDA to provide project status update to help ascertain success of the project. We advised for a project monitoring committee to be setup for this purposes
22 | Consultancy for the Deployment of Public Transportation Management System | Providing Consultancy service for the deployment of Public Transportation Management System for the Ministry of Transport Plateau State. | Ministry of Transportation, Unsolicited Project by Access Solution | 1. Agency reviewed all submissions by the private partner 2. Agency has requested for project status report, setting up of project committee and signed MOU from the ministry. | Yet to receive the current status of the project and a copy of the MOU from Ministry of Transport. We advocate for a project monitoring committee.
23 | The Development, Construction and Commisioning of an Integrated Waste Management, Recycling and Energy Genetration System | This project includes the collection, transportion, treatment and disposal of waste, together with monitoring and regulation of the waste management process and waste-related laws, technologies, and economic mechanisms. | Ministry of Environment, Ministry of Water Resources and Energy, Unsolicited: International Local Development Consortium Nigeria Limited | 1. It was iniated by a private partner with claimed international affiliation but no local operations, who were focused on waste to energy, ILDC international. PLSG revised intended project for in waste collection and disposal. Agency reassessed and confirmed proposeed dumpsite land titles with Ministry of Lands. Private party ILDC could not demonstrate technical capacity and Financial capacity for this project 2. Reviewed detailed soft copies of documents revised for the collection and disposal of waste by partner which signed an MoU which has currently teminated due expected performance timelines outlined in MOU. | 1. Documents submitted strictly developed by Private Partner which was reviewed. 2. Project Stopped due to insufficient demonstration of capacity by Private Partner to execute project. 3. Agency advised Ministry of Environment to conduct preliminary needs asssess, scoping and clear defined concept note for the project to aid other project preparation assessments needed by Agency to assist in properly supporitng this project development and structuring.
24 | Establishment of Tomato Processing Factory | Establishment of a tomato paste processing factory | PIPC, Bokkos Local Government Council, Unsolicited proposal by Sonia Farms and Integrated Services | 1. The Agency received a letter of interest from Sonia Farms who are Tomoto value add processors needing minimum 2000 Hectares of Land plus water body for the relocation of thier $15 million factory from Taraba to Plateau State. 2. Requested for preliminary information on BARC Farms with over 4000 Heactares plus a dam as most suitable location as investor was not keen on partnering directly with Government. Agency deemed PIPC as best fit as a SOE but never got any feedback or interest from PIPC on this proposition. | 1.Agency communited to private partner of no availability of minimum 2000 heactares of land plus water body for its operations. The project currently suspended to be located on the Plateau. Agency also attempted to locate similar land mass with Bokkos LGA chairman but still not progress was made to identify suitable location for this factory relocation.
25 | Plateau State Liaison Office No. 17 Race Course Root and No.18 Yakubu Avenue (Kaduna Project) | Development of the Plateau State Property in Kaduna into Residential Units and Offices with Attendant infrastructure | Secretary to Government of State, Ministry of Justice, Kaduna State Government, MC Dreams Ltd. | 1. Agency assessed all documents pertaining to this property, reviwed and advised the SGS on the necessary actions 2. Agency assessed and advised on all other state assets in Kaduna state with the Liason officer in charge to assess the current state and location of the property 3. Agency communicated failure by Private partner to adhere to terms for partnership and not fulfill all obligations required. Agency recommended immediate termination of agreement and stay action on the development on site etc. | Payment of outstanding obligations to Kaduna state government were paid by last administration and the assets CofO was issued currently with the SGS office for this asset. 2. Construction on the site by Private partner was stopped and documents provided were falsified. It is recommended that an assessment of the damage as well as investment currently made by the private partner be carried out. Amicable measures to be carried out to resolve current bottleneck on this agreement and a new concept for the property be revisited to ensure adequate value is acheived by the State for this prime asset.
26 | Lease of Plateau Hotel | Development and management of the Plateau Hotel Complex | Plateau State Tourism Corporation, Unsolicited proposal by Plateau Wonderland NIG Ltd | 1. The Agency received and reviewed documents from the private partner 2. Reviewed title documents on the asset and yet to ascertain current value plus conduct best use of asset analysis compared to the offer of N15million annual lease payment by this private partner. | Agency to work with Plateau State Tourism Corporation to ascertain current asset valuation and develop concept note of posible various other infrastructural developments that can maximise use of asset in current prime location. Agency is proposing a modern mixed commercial use development to make it more viable and attractive to investors. Agency Ranks this as a Top Priority Project.
28 | PRTV- Delmedia Engagement | Transformation with PRTv to Transition from an analogue to digital transmission infrastructure to the Direct to a Home (DTH) Platform as well as creative industry studio development | Unsolicited proposal by Delmedia Productions | Private partner submitted a project proposal which was reviewed by the Agency. The Ministry of Information did not wish to engage on this project as it was not certain the implications to thier existing jobs. The Agency deems this a potentially impactful innovation and initiative which will both modernize the PRTv operations as well as impact the creative industry which Jos is known for. | The concept note and possible favourable criteria to be defined by the Ministry of Information on how such a proposition will be mutually beneficial to PLSG as well as upgrade the old infrastructure and make adequate use of the surrounding lands in PRTv for other developments.